## Sheet1
GAM403: Assessment 2 Milestones | Project: Sumo-Soccer | Developer: Ashley Hall
Milestone | Description | Due Date | Days Left | Completion Date | Notes
Base Character Movement | Core system for two directional movement. Get speed, momentum, and controls in general feeling tight and responsive. | 2019-11-07 | -1 | 2019-11-05
Two Player input (keyboard) | Edit the InputManager to accommodate a second player. Modify movement code to facilitate the different inputs. | 2019-11-09 | 1 | 2019-11-05
Level blockout | Use basic geometry to define the basic playable area - setup basic colliders for the level bounds. | 2019-11-11 | 3 | 2019-11-04
Player/Ball physics & interactions | Play test how the two players interact with eachother physically. Add the ball game object and test/refine interaction through RigidBody settings. | 2019-11-11 | 3
Scoring and penalties | Add a point to a player when the ball enters the goal zone or if a player is pushed/falls out of the arena. | 2019-11-15 | 7
Winning and round management | Using new scoring system, reset the arena every time a point is scored. Monitor the score and when a player reaches 3 points declare them the winner. | 2019-11-16 | 8
Basic UI menu/pause | Add start menu (play button and basic instructions) and pause screen with text that can be modified to suit the pause or victory screen. | 2019-11-18 | 10
Playtesting & movement polish pass | With the core gameplay elements in play, playtest the game and get feedback on the movement and player interaction. Modify accordingly. | 2019-11-20 | 12
Charge attack & pickups | Add linear charge attack with cooldown. Charge attack should slow down steering until the charge is finished. Add simple pickups that temporarily increase speed, weight, size, etc) | 2019-11-25 | 17
Character beauty pass | Refine visual fidelity of players and ball. Add particle effects for big hits and powerups. | 2019-11-30 | 22
Level beauty pass | Refine visual fidelity of level. If time is short, consider sourcing assets from the Unity Asset Store. | 2019-11-30 | 22
Formulas:
Days Left = IF([Developer: Ashley Hall]<>"",[Developer: Ashley Hall]-TODAY(),"")